FlyToday Oy

REQUEST FOR PROPOSAL (RFP)

Enterprise Engineering Data Migration to Siemens Teamcenter

RFP Number: FT-PLM-RFP-2026-014

Document Version: V1.00

Date of Issue: 30 July 2026

Issued by: FlyToday Oy, Helsinki, Finland

Contact Person: Susanta Kumar Saha

Confidential and proprietary to FlyToday Oy

Table of Contents

1. Executive Summary	3

2. Objectives	3

3. Background	4

4. Scope of Work	4

4.1 Object-Level Migration Requirements	5

5. Requirements	6

5.1 Functional Requirements	6

5.2 Data Quality Requirements	6

5.3 Security Requirements	7

6. Timeline Expectations	7

7. Project Structure and Communication	8

8. Proposal Requirements	9

9. Selection Criteria and Selection Terms	10

10. Appendices	10

Appendix A – Indicative Data Volumes	10

Appendix B – Definitions	11

Appendix C – Compliance Matrix Instructions	11

Appendix D – Clarification Process	11

Appendix E – Baseline Assumptions and Dependencies	11

Appendix F – Proposal Approval and Version History Template	11

Appendix G – Consolidated Deliverables and Acceptance Summary	12

Appendix H – Supplier Reference and Experience Template	12

Appendix I – Submission Checklist	12

FlyToday Oy

REQUEST FOR PROPOSAL (RFP)

Enterprise Engineering Data Migration to Siemens Teamcenter

| RFP Reference | FT-PLM-RFP-2026-014 |
| --- | --- |
| Issuing Organization | FlyToday Oy, Helsinki, Finland |
| Industry | Aerospace — Design and Manufacture of Passenger Aircraft, Cargo Aircraft, Fighter Jets, Seaplanes and Amphibious Aircraft |
| Date of Issue | 30 July 2026 |
| Deadline for Clarification Questions | 1 August 2026, 7:00 EET (10:00 BST) |
| Proposal Submission Deadline | 1 August 2026, 10:00 EET (13:00 BST) |
| Submission Address | Susanta Kumar Saha – susanta.kumar@bjitgroup.com |
| Single Point of Contact | Category Manager, IT & Engineering Systems Procurement |

Confidentiality: This RFP and all information contained herein are confidential and proprietary to FlyToday Oy. Distribution, reproduction or use for any purpose other than preparation of a proposal is prohibited. Receipt of this RFP is subject to execution of the Non-Disclosure Agreement referenced in Section 5.3.

# 1. Executive Summary

Purpose: This Request for Proposal invites qualified suppliers to submit binding technical and commercial proposals for the migration of engineering data from multiple legacy PDM/PLM systems into a centralized Siemens Teamcenter environment and its surrounding system integrations.

Description: FlyToday Oy, a leading European aerospace manufacturer, is consolidating engineering information currently distributed across Autodesk Vault, SolidWorks PDM, SmarTeam, shared network drives and custom PDM systems into a single, centrally managed Siemens Teamcenter platform. The migration covers approximately 120000 items with their revisions and bills of material, and approximately 250000 documents (Office documents, PDF, DWG, DXF and 3D CAD models), based on preliminary system extracts performed in Q1 2026. The selected Supplier shall deliver a complete, end-to-end migration solution comprising assessment, extraction, transformation, automation with reusable solution and tooling, validation, loading, testing, deployment, hypercare, documentation and knowledge transfer.

Supplier Expectations: Suppliers shall demonstrate proven aerospace PLM migration experience, a highly automated migration factory approach with minimal manual effort, effective use of AI-assisted capabilities, and the capacity to complete production migration by 31 December 2026. From 1 January 2027, FlyToday Oy will declare Siemens Teamcenter the single source of engineering data.

Required Deliverables: A complete technical and commercial proposal in accordance with Section 8, submitted no later than 1 August 2026, 10:00 EET.

Acceptance Criteria: Proposals shall be complete, compliant with Section 8, and signed by an authorized representative. Non-compliant or late proposals may be rejected without evaluation.

# 2. Objectives

Purpose: To define the business and technical objectives against which the migration program and the Supplier's performance will be measured.

Description: The migration objectives of FlyToday Oy are as follows:

- Consolidate all engineering data from legacy PDM/PLM systems and unmanaged repositories into a single, easily manageable Siemens Teamcenter environment.

- Preserve data integrity, completeness, traceability and configuration context (revisions, versions, lifecycle states, release statuses, relationships and structures) throughout the migration.

- Maximize automation with reusable solution and minimize manual migration effort through repeatable, tool-based migration processes, including AI-assisted classification, mapping and data quality analysis.

- Ensure surrounding enterprise systems remain synchronized with migrated data and documents after cutover.

- Decommission legacy systems following successful migration and business acceptance.

Supplier Expectations: Supplier shall structure its solution, plan and pricing to demonstrably achieve each objective and shall state any objective it considers at risk, together with mitigation measures.

Required Deliverables: Objective-by-objective response in the technical proposal, including measurable success criteria proposed by the Supplier.

Acceptance Criteria: Each objective is addressed with a concrete, verifiable approach. Final business acceptance criteria will be jointly refined and confirmed with the selected Supplier after onboarding.

# 3. Background

Purpose: To provide Suppliers with the context of the current engineering data landscape.

Description: FlyToday Oy operates five business units: Passenger Aircraft, Cargo Aircraft, Fighter Jet, Seaplane and Amphibious Aircraft. Over two decades of growth and acquisitions, each business unit has adopted its own engineering data management practices. The current landscape comprises at least the following source environments; additional departmental repositories and custom PDM databases may be identified during the assessment phase:

| Source System | Primary Business Units | Content (indicative) |
| --- | --- | --- |
| Autodesk Vault | Cargo Aircraft, Seaplane | Inventor/AutoCAD models, 2D drawings, item records, BOMs |
| SolidWorks PDM | Passenger Aircraft, Amphibious Aircraft | SolidWorks models, assemblies, drawings, EBOMs, specifications |
| SmarTeam | Fighter Jet | CATIA data, engineering documents, lifecycle-managed items, custom object types (partially undocumented) |
| Shared network drives | All business units | Office documents, PDFs, specifications, legacy scans, loose CAD files |
| Custom PDM systems | Fighter Jet, Cargo Aircraft | In-house developed databases for item master, change records and document registers |

Supplier Expectations: Supplier shall treat all volume and system information in this RFP as indicative and shall confirm actual volumes, object types and data conditions during the assessment phase. Supplier shall describe its approach to discovering undocumented data structures and repositories.

Required Deliverables: A statement of assumptions and a list of clarification questions submitted per the timetable in Section 6.

Acceptance Criteria: Supplier demonstrates understanding of multi-source aerospace data landscapes and identifies material risks and information gaps.

# 4. Scope of Work

Purpose: To define the services and data scope for which proposals are requested.

Description: The Supplier shall deliver a complete migration solution covering the following phases:

| Phase | Scope |
| --- | --- |
| 1. Assessment | Source system analysis, data profiling, volume confirmation, data quality baseline, migration strategy and cutover concept |
| 2. Design & Mapping | Source-to-target data mapping, transformation rules, migration architecture, tooling design, target data model alignment with FlyToday's Teamcenter configuration |
| 3. Build & Automation | Development and configuration of extraction, transformation, validation and loading tooling; automation of repetitive migration tasks; AI-assisted mapping/classification where applicable |
| 4. Pilot Migrations | Respondents must describe their proposed approach to conducting a pilot (small-batch) migration that validates all in-scope data types and business scenarios. The response should detail testing methodologies, validation controls, and the process for obtaining business stakeholder sign-off prior to full migration. |
| 5. Production Migration & Cutover | Production data migration, cutover execution per the Supplier-proposed downtime window, go-live support, synchronization of surrounding systems |
| 6. Hypercare | Post-go-live support, defect resolution, residual data corrections, exception handling |
| 7. Documentation & Knowledge Transfer | Migration documentation, runbooks, tool handover, training and knowledge transfer to FlyToday personnel |

Data objects in scope. Supplier shall migrate the following engineering objects, including all associated metadata, files and relationships:

| Category | Objects |
| --- | --- |
| Item data | Item Master; Attributes; Classification; Revisions; Versions; Lifecycle States; Release Status |
| Documents | Document objects; PDF; Office Documents; Specifications; Engineering Documents |
| CAD data | CAD Metadata; 2D Drawings; 3D CAD Models; Assemblies; CAD Structure (including inter-part references and drawing-to-model links) |
| Product structure | BOM; EBOM; MBOM (where applicable in the source systems); Relationships between items, documents and CAD objects |
| Other | Custom Objects (including custom object types identified during assessment); historical change objects may be included subject to feasibility assessment |

Out of scope: Teamcenter platform implementation and configuration (delivered under a separate contract), ERP master data cleansing, and physical archival of legacy hardware.

Supplier Expectations: Supplier shall propose a phased, repeatable migration approach with clearly defined entry and exit criteria per phase. Supplier shall propose the production cutover approach and downtime window, minimizing disruption to engineering operations.

Required Deliverables: Migration strategy; data mapping specifications; migration tooling; trial migration reports; validation reports; cutover plan; hypercare plan; final migration report; runbooks; training material.

Acceptance Criteria: All in-scope objects migrated, validated and reconciled per Section 5.2; surrounding systems synchronized; deliverables approved by FlyToday in writing.

## 4.1 Object-Level Migration Requirements

Supplier shall migrate each of the following engineering objects in accordance with the stated requirement. This matrix is indicative; Supplier shall confirm and refine it during the assessment phase.

| Engineering Object | Migration Requirement |
| --- | --- |
| Item Master | Supplier shall migrate all item master records with unique identifiers, descriptions and governing attributes, preserving source cross-references for traceability. |
| Document / PDF / Office Documents | Supplier shall migrate document objects with their native and rendered files (PDF, DOC/DOCX, XLS/XLSX, etc.), preserving document numbers, titles and metadata. |
| Specifications / Engineering Documents | Supplier shall migrate specifications and engineering documents with their linkage to the governing items and revisions. |
| CAD Metadata | Supplier shall extract and map CAD file properties and attributes to the corresponding Teamcenter dataset and item revision attributes. |
| 2D Drawings | Supplier shall migrate 2D drawings (native and neutral formats such as DWG/DXF/PDF), preserving drawing-to-model and drawing-to-item associativity. |
| 3D CAD Models | Supplier shall migrate native 3D models for Inventor, SolidWorks and CATIA sources, preserving datasets, named references and viewable. |
| Assemblies / CAD Structure | Supplier shall migrate assembly structures so that all components resolve, and inter-part and external references remain intact and openable in Teamcenter. |
| BOM / EBOM / MBOM | Supplier shall migrate BOM and EBOM structures (and MBOM where present) with quantities, find numbers, reference designators and effectivities. |
| Relationships | Supplier shall migrate item-to-item, item-to-document and item-to-CAD relationships, preserving referential integrity at both ends. |
| Revisions / Versions | Supplier shall migrate revision and version chains in correct chronological and released-state sequence per the agreed retention policy. |
| Lifecycle States / Release Status | Supplier shall map source lifecycle and release states to the target Teamcenter lifecycle and status model, preserving released/obsolete integrity. |
| Classification / Attributes | Supplier shall migrate classification hierarchies and all mandatory and custom attributes, with value mapping and unit normalization. |
| Custom Objects | Supplier shall migrate custom object types identified during assessment, mapping them to appropriate Teamcenter constructs, or flag them for disposition. |

# 5. Requirements

Requirements identified with “shall” are mandatory. Supplier shall complete the compliance matrix (Appendix C) indicating full, partial or non-compliance for each requirement, with explanatory comments.

## 5.1 Functional Requirements

| Req. ID | Requirement |
| --- | --- |
| FR-01 | Supplier shall extract complete data sets (metadata, files, structures, relationships) from Autodesk Vault, SolidWorks PDM, SmarTeam, shared drives and the custom PDM systems, including object types discovered during assessment. |
| FR-02 | Supplier shall transform source data to FlyToday's Teamcenter data model, which is substantially defined and will be baselined during the design phase. |
| FR-03 | Supplier shall migrate 3D CAD models, assemblies and 2D drawings with full associativity, such that assemblies resolve their components and drawings resolve their model references in Teamcenter. |
| FR-04 | Supplier shall migrate BOM and EBOM structures, and MBOM structures where applicable, preserving quantities, find numbers, effectivities and structure-level attributes. |
| FR-05 | Supplier shall preserve revision and version history, lifecycle states and release statuses, mapped to the Teamcenter lifecycle and workflow model. |
| FR-06 | Supplier shall migrate classification data and all mandatory and custom attributes, including attribute value mapping and unit normalization. |
| FR-07 | Supplier shall migrate relationships between items, documents, CAD objects and custom objects, preserving referential integrity. |
| FR-08 | Supplier shall provide a migration factory with automated, repeatable, restartable and auditable ETL pipelines; manual data manipulation shall be limited to documented exception handling. |
| FR-09 | Supplier shall describe and quantify the use of AI-assisted capabilities (e.g., automated attribute mapping, duplicate detection, document classification, anomaly detection) within the migration process. |
| FR-10 | Supplier shall support delta/incremental migration so that data created or changed in legacy systems during the migration period is captured up to cutover. |
| FR-11 | Supplier shall ensure that, after migration, surrounding systems integrated with Teamcenter remain synchronized with the migrated data and documents. |
| FR-12 | Supplier shall provide a rollback and contingency approach for the production cutover. |
| FR-13 | Supplier shall execute at least two full-volume trial migrations per source system prior to production migration. |
| FR-14 | Supplier shall provide documentation and knowledge transfer enabling FlyToday to operate and audit the migrated environment and any residual tooling. |

Required Deliverables: Requirement compliance matrix; solution architecture; tooling description; automation coverage statement (percentage of records processed without manual touch).

Acceptance Criteria: Demonstrated compliance in trial migrations; automation coverage meeting or exceeding the level committed in the proposal.

## 5.2 Data Quality Requirements

Supplier shall explain, in its technical proposal, its methodology, tooling and deliverables for each of the following:

| Req. ID | Requirement |
| --- | --- |
| DQ-01 | Duplicate detection strategy across and within source systems, including AI/similarity-based detection for items, documents and CAD files, and the proposed resolution workflow. |
| DQ-02 | Data profiling of all source repositories during assessment, establishing a quantified data quality baseline. |
| DQ-03 | Metadata completeness analysis and enrichment approach for records with missing or inconsistent metadata. |
| DQ-04 | Mandatory attribute validation against the Teamcenter data model prior to load, with automated rejection/repair handling. |
| DQ-05 | Broken CAD reference detection (missing components, dangling drawing references, unresolved external references) and remediation approach. |
| DQ-06 | Missing document handling, including detection of registered documents whose files are absent or corrupt, and the proposed disposition process. |
| DQ-07 | Relationship validation ensuring all migrated relationships resolve to valid objects at both ends. |
| DQ-08 | CAD assembly validation, including automated open/regeneration testing and structure comparison between source and target. |
| DQ-09 | Revision consistency validation (sequence, effectivity, released-state integrity) between source and target. |
| DQ-10 | Version consistency validation, including handling of source revisions subject to the retention policy for obsolete revisions, which is currently pending final approval by FlyToday. |
| DQ-11 | File checksum validation confirming bit-level integrity of every migrated file. |
| DQ-12 | Data reconciliation methodology, with object counts, attribute-level sampling and structure comparison per migration run. |
| DQ-13 | Migration dashboard providing FlyToday near-real-time visibility of migration progress, quality KPIs and exception volumes. |
| DQ-14 | Exception reports per migration run, categorized by severity, with root cause and disposition. |
| DQ-15 | Final reconciliation reports evidencing completeness and correctness, suitable for aerospace quality and airworthiness audit purposes. |

Acceptance Criteria: Quantitative quality thresholds (e.g., 100% checksum match, 100% relationship resolution, agreed thresholds for metadata completeness) shall be proposed by the Supplier and jointly confirmed during the assessment phase.

## 5.3 Security Requirements

| Req. ID | Requirement |
| --- | --- |
| SEC-01 | Supplier shall execute FlyToday's Non-Disclosure Agreement (NDA) prior to receiving any production data or system access. |
| SEC-02 | Supplier shall operate an information security management system certified to ISO/IEC 27001, and shall provide the certificate with its proposal. |
| SEC-03 | Supplier shall access FlyToday systems exclusively via FlyToday-approved secure VPN connections with multi-factor authentication. |
| SEC-04 | Supplier shall use secure, encrypted file transfer mechanisms (SFTP or equivalent, minimum AES-256 in transit and at rest) for all data movement; removable media are prohibited. |
| SEC-05 | Supplier shall implement role-based access control and least-privilege principles for all project personnel, with named-user access, joiner/leaver processes and access logs available to FlyToday on request. |
| SEC-06 | Supplier shall comply with the EU General Data Protection Regulation (GDPR) for any personal data processed, and shall execute a Data Processing Agreement where applicable. |
| SEC-07 | Supplier shall process and store FlyToday data only in facilities and jurisdictions approved by FlyToday, and shall comply with applicable export control regulations relevant to defense-related data of the Fighter Jet business unit. |
| SEC-08 | Supplier shall report any suspected security incident affecting FlyToday data within 24 hours and shall support forensic investigation. |

Required Deliverables: Signed NDA; ISO 27001 certificate; security concept describing VPN, transfer, access control and data handling; incident response summary.

Acceptance Criteria: Security concept approved by FlyToday Information Security prior to any data access; compliance maintained throughout the engagement.

# 6. Timeline Expectations

Purpose: To communicate the procurement timetable and the mandatory migration completion date.

| Milestone | Date |
| --- | --- |
| RFP issued | 30 July 2026 |
| Clarification questions due | 1 August 2026, 07:00 EET (10:00 BST) |
| FlyToday responses to all Suppliers | 1 August 2026, 05:45 EET (8:45 BST) |
| Proposal submission deadline | 1 August 2026, 10:00 EET (13:00 BST) |
| Supplier presentations / evaluation | 1 August 2026, 11:00-14:30 EET (14:00-17:30 BST) |
| Supplier selection and contract award | 3 August 2026 |
| Project kick-off | 10 August 2026 |
| Production migration completed | 31 December 2026 (mandatory) |
| Teamcenter declared single source of engineering data | 1 January 2027 |
| Hypercare period | January – February 2027 (duration to be proposed) |

Supplier Expectations: Supplier shall provide a detailed work plan demonstrating credible achievement of the 31 December 2026 completion date, including resource loading, dependencies on FlyToday, and the proposed production cutover and downtime window. Supplier shall identify schedule risks and mitigations.

Required Deliverables: Gantt-level project plan; milestone list with entry/exit criteria; cutover and downtime proposal.

Acceptance Criteria: Plan is achievable, resourced and consistent with the mandatory completion date; interim milestones accepted by FlyToday at contract signature.

# 7. Project Structure and Communication

Purpose: To define governance, roles and communication expectations for the engagement.

Description: The program will be governed by a joint Steering Committee meeting monthly, an FlyToday Program Manager, and business-unit data owners. Allocation of data ownership responsibilities across the five business units is being finalized and will be communicated during the assessment phase.

Supplier Expectations: Supplier shall:

- Provide a dedicated Project Manager as single point of contact, a lead migration architect, and named key personnel who shall not be substituted without FlyToday's written approval.

- Conduct weekly status meetings and provide written weekly progress reports covering progress, quality KPIs, risks, issues and upcoming activities.

- Maintain a joint RAID log (risks, assumptions, issues, dependencies) and an agreed escalation path with defined response times.

- Use English as the project language for all deliverables, meetings and documentation.

- Work within FlyToday's project collaboration environment for document management and issue tracking.

Meeting cadence. Supplier shall support, at minimum, the following governance and communication rhythm:

| Forum | Frequency | Participants / Purpose |
| --- | --- | --- |
| Steering Committee | Monthly | Executive sponsors, Programme Manager, Supplier Engagement Lead — strategic direction, escalations, milestone acceptance |
| Project status meeting | Weekly | Project Managers and workstream leads — progress, KPIs, risks, issues, next actions |
| Technical working session | As required | Migration architects and data owners — mapping, transformation and validation topics |
| Cutover readiness review | At each gate | Both parties — go/no-go assessment against entry/exit criteria |
| Hypercare stand-up | Daily (hypercare) | Support team and FlyToday leads — defect triage and resolution tracking |

Hypercare service levels. During the hypercare period, Supplier shall meet the following minimum response and resolution targets. Final service levels shall be confirmed at contract signature.

| Severity | Definition | Response Time | Target Resolution |
| --- | --- | --- | --- |
| Critical (S1) | Migrated data blocks production engineering; no workaround | 1 hour | 1 business day |
| High (S2) | Significant data defect affecting a business unit; workaround exists | 4 hours | 3 business days |
| Medium (S3) | Localized data or metadata defect with limited impact | 1 business day | 10 business days |
| Low (S4) | Cosmetic or minor discrepancy | 2 business days | Next release |

Required Deliverables: Project organization chart; RACI matrix; communication plan; escalation procedure; CVs of key personnel; hypercare support plan with agreed service levels.

Acceptance Criteria: Governance model agreed at kick-off; reporting operational from week one of the engagement; hypercare service levels met and evidenced in support reports.

# 8. Proposal Requirements

Purpose: To define the mandatory content and format of proposals.

Description: For pricing purposes, Suppliers shall base their proposals on the following indicative scope: approximately 120000 items including their revisions and bills of material, and approximately 250000 documents (DOC, PDF, DWG, DXF and 3D models), distributed across the source systems described in Section 3. After migration, the surrounding systems must be synchronized with the migrated data and documents. Supplier shall state unit-rate or volume-band mechanisms for handling deviation from these indicative volumes.

Supplier Expectations: The proposal shall be structured strictly in the following twelve (12) sections, in the order listed. Each section shall be separately identifiable and clearly headed. Supplier shall also complete the requirement compliance matrix (Appendix C) and provide its ISO 27001 certificate and sign NDA as annexes.

| # | Proposal Section | Mandatory Content |
| --- | --- | --- |
| 1 | Executive Summary | Overview of the proposed solution, confirmation of compliance with this RFP, and key differentiators including automation with reusable solution for future migration and AI-assisted capabilities |
| 2 | Scope | Supplier's understanding and confirmation of the migration scope: in-scope source systems, engineering objects (per Section 4), volumes, and post-migration synchronization of surrounding systems |
| 3 | Out of Scope | Explicit statement of exclusions, boundaries and any activities the Supplier assumes are the responsibility of FlyToday or third parties |
| 4 | Migration Solution Proposal | Migration methodology and architecture; extraction, transformation, validation and loading tooling; automation approach and coverage; AI-assisted capabilities; named technologies, products and versions comprising the proposed tech stack |
| 5 | Estimation | Effort estimates by phase and role, basis of estimate, assumptions, automation coverage (percentage of records processed without manual touch), and fixed price per phase with unit rates for volume deviations and change requests |
| 6 | Schedule with Key Milestones | Gantt-level plan demonstrating completion by 31 December 2026, key milestones with entry/exit criteria, trial-migration runs, and the proposed cutover and downtime window |
| 7 | Meeting Cadence | Proposed governance and meeting rhythm (steering, weekly status, working sessions), participants and decision forums |
| 8 | Reporting | Progress and quality reporting approach, KPIs, migration dashboard, and exception/reconciliation reporting |
| 9 | Risk / Issue / Dependency | Initial RAID register: key risks with mitigations, issues, and dependencies on FlyToday and third parties |
| 10 | Approval & Version History | Document approval sign-off block and version history table for the proposal itself |
| 11 | Team Structure | Organization chart, RACI, and CVs of key personnel (Project Manager, lead migration architect and other key roles) |
| 12 | Resource Allocation Plan | Resource loading by role and phase over the project timeline, including on-site/off-site split and named key personnel commitments |

Commercial and payment structure. Supplier shall present a fixed-price commercial proposal with payments tied to accepted deliverables. Proposals shall be structured against the payment terms set out below, which Supplier may comment on. Payments for the migration phase shall be released on time following successful completion of the relevant migration activities within the agreed timeline and acceptance by FlyToday Oy. Payments for hypercare phases shall be invoiced and settled separately monthly basis.

Change control. Any change to scope, volume bands or the target data model shall be managed through a formal written change control procedure, with impact on cost and schedule agreed by both parties before work proceeds.

Required Deliverables: One PDF proposal document (maximum 20 pages excluding CVs, certificates and annexes) structured in the twelve sections above, submitted to procurement.plm@flytoday.fi by 1 August 2026, 13:00 EET. Proposals shall remain valid for ninety (90) days.

Acceptance Criteria: Proposals containing all twelve sections, with the compliance matrix and required annexes, submitted on time and duly signed, will be admitted to evaluation.

# 9. Selection Criteria and Selection Terms

Purpose: To communicate how proposals will be evaluated and the terms governing this procurement.

Description: Admitted proposals will be evaluated by a cross-functional evaluation committee against the following weighted criteria:

| Evaluation Criterion | Weight | Evaluation Basis |
| --- | --- | --- |
| Cost effectiveness (total cost of ownership, pricing transparency) | 25% | Commercial proposal, unit rates, assumptions |
| Degree of automation / minimization of manual migration effort | 20% | Automation coverage statement, tooling maturity, trial approach |
| Ability to deliver on time (by 31 December 2026) | 20% | Project plan credibility, resourcing, references |
| Use of AI-powered capabilities in the migration process | 15% | Concrete, verifiable AI use cases and their measurable benefit |
| Relevant experience and references (aerospace / regulated industry) | 10% | Reference projects, key personnel CVs |
| Data quality and validation methodology | 10% | Response to Section 5.2 |

Selection Terms: The following terms apply:

- FlyToday Oy reserves the right to accept or reject any proposal in whole or in part, to negotiate with one or more Suppliers, to request best-and-final offers, or to cancel this RFP at any time without liability.

- FlyToday Oy will not reimburse any costs incurred in preparing or presenting proposals.

- Shortlisted Suppliers may be invited to present their solution and demonstrate their migration tooling during the evaluation period.

- Contract award is subject to successful contract negotiation and FlyToday internal approvals. This RFP does not constitute an offer or commitment to purchase.

- The engagement is expected to be contracted as a fixed-price agreement with milestone-based payments tied to accepted deliverables.

Acceptance Criteria: The Supplier achieving the highest weighted total score, and successfully concluding negotiations, will be awarded the contract.

# 10. Appendices

## Appendix A – Indicative Data Volumes

| Object Category | Indicative Volume (preliminary, to be confirmed during assessment) |
| --- | --- |
| Items (with revisions and BOMs) | ~120000 |
| Documents (DOC, PDF, DWG, DXF, 3D models) | ~250000 |
| Source systems | 5 system families per Section 3; final count subject to assessment |
| File volume (estimated) | ~6 TB across all repositories |

## Appendix B – Definitions

| Term | Definition |
| --- | --- |
| EBOM / MBOM | Engineering / Manufacturing Bill of Materials |
| ETL | Extraction, Transformation and Loading |
| Hypercare | Intensified post-go-live support period |
| Migration Factory | Industrialized, automated, repeatable migration process and toolchain |
| Surrounding systems | Enterprise systems integrated with Teamcenter that consume or exchange engineering data |
| Cutover | Controlled transition of production data and users from legacy systems to Teamcenter |

## Appendix C – Compliance Matrix Instructions

Supplier shall reproduce every requirement ID from Sections 5.1–5.3 in a table with columns: Requirement ID; Compliance (Full / Partial / None); Comment / Solution Reference. Partial or non-compliance shall be explained, including any proposed alternative.

## Appendix D – Clarification Process

Questions shall be submitted in writing to procurement.plm@flytoday.fi by the deadline in Section 6, quoting the RFP reference and section number. Answers will be distributed to all invited Suppliers without identifying the source of the question. Verbal information shall not be binding on FlyToday Oy.

Supplier shall submit clarification questions using the template below.

| # | RFP Section | Question / Assumption | Impact if Unresolved |
| --- | --- | --- | --- |
| 1 |  |  |  |
| 2 |  |  |  |
| 3 |  |  |  |

## Appendix E – Baseline Assumptions and Dependencies

The following baseline assumptions and dependencies apply to this RFP. Supplier shall confirm, challenge or supplement each item in its proposal and during the assessment phase.

| # | Item | FlyToday Responsibility / Note |
| --- | --- | --- |
| A1 | Data volumes and file sizes are preliminary estimates from Q1 2026 extracts | To be confirmed by profiling during assessment |
| A2 | The Teamcenter target platform is delivered under a separate implementation contract | FlyToday to provide environments, data model and integration endpoints |
| A3 | FlyToday will provide timely access to source systems, subject-matter experts and business-unit data owners | Data ownership allocation being finalized |
| A4 | Non-production environments of adequate capacity will be available for trial migrations | Provided by FlyToday / implementation partner |
| A5 | The retention policy for obsolete revisions and historical change objects will be approved before production migration | FlyToday to confirm |
| A6 | Surrounding-system interfaces required for post-migration synchronization will be specified during design | Joint responsibility |

## Appendix F – Proposal Approval and Version History Template

Supplier shall include, in its proposal, a completed approval sign-off block and version history table in the format below.

| Version | Date | Author | Summary of Change |
| --- | --- | --- | --- |

| Approval Role | Name | Signature / Date |
| --- | --- | --- |
| Supplier — Authorized Representative |  |  |
| Supplier — Project Sponsor |  |  |

## Appendix G – Consolidated Deliverables and Acceptance Summary

The table below consolidates the key deliverables by phase and the basis on which FlyToday will accept them. Supplier shall confirm this list and map each deliverable to its proposed schedule and payment milestones.

| Phase | Key Deliverables | Acceptance Basis |
| --- | --- | --- |
| Assessment | Source analysis report; data profiling and quality baseline; confirmed volumes; migration strategy | FlyToday review and written sign-off of strategy and baseline |
| Design & Mapping | Source-to-target mapping specifications; transformation rules; migration architecture; tooling design | Mapping and architecture approved against the baselined data model |
| Build & Automation | Configured extraction, transformation, validation and loading tooling; automation and AI components | Tooling demonstrated; automation coverage meets committed level |
| Pilot Migration | A successfully migrated small batch of engineering data from the legacy system, complete with data mapping, validation report, and defect log. | All in-scope engineering data is migrated completely and accurately with no critical defects and formally signed off by business stakeholders. |
| Production & Cutover | Production migration; cutover execution; surrounding-system synchronization | Go-live accepted; reconciliation and checksum validation passed |
| Hypercare | Support reports; defect resolution log; residual data corrections | Service levels met; open defects within agreed thresholds |
| Documentation & KT | Migration documentation; runbooks; tool handover; training and knowledge transfer | Documentation accepted; FlyToday personnel trained and self-sufficient |

## Appendix H – Supplier Reference and Experience Template

Supplier shall provide at least three (3) comparable PDM/PLM migration references, preferably in aerospace or other regulated industries, using the template below. FlyToday reserves the right to contact the named references.

| Field | Reference 1 | Reference 2 / 3 |
| --- | --- | --- |
| Client organization and industry |  |  |
| Source and target PLM systems |  |  |
| Data volume migrated (items / documents) |  |  |
| Automation coverage achieved |  |  |
| AI-assisted capabilities applied |  |  |
| Project duration and outcome |  |  |
| Reference contact (name, role, email) |  |  |

Supplier declaration. Supplier shall confirm that the information provided in its proposal, including references and certifications, is accurate and that the named key personnel will be available for the engagement. Misrepresentation may result in disqualification.

## Appendix I – Submission Checklist

Supplier shall confirm inclusion of each item below before submitting its proposal.

| # | Submission Item | Included |
| --- | --- | --- |
| 1 | Proposal structured in the twelve sections defined in Section 8 |  |
| 2 | Completed requirement compliance matrix (Appendix C) |  |
| 3 | Signed Non-Disclosure Agreement |  |
| 4 | Valid ISO/IEC 27001 certificate |  |
| 5 | Key personnel CVs |  |
| 6 | At least three references (Appendix H) |  |
| 7 | Fixed-price commercial proposal with milestone plan |  |
| 8 | Clarification assumptions and any contract exceptions |  |

End of Request for Proposal. FT-PLM-RFP-2026-014. This document comprises the complete RFP issued by FlyToday Oy. Suppliers shall acknowledge receipt and confirm their intent to respond by return email to the Single Point of Contact.