## RAP
RAP (from Scratch)
# | Resource | Rank | Unit price/hour in Euro | M1 | M2 | Total Efforts (mm & Cost) | Total cost in Euro
1 | Project Manager | 6 | 1 | 25% | 25% | 0.5 | 80
2 | Sr. UI/UX Designer | 5 | 1 | 100% |  | 1 | 160
3 | Lead Software Engineer (Backend) : Spring Boot | 5 | 1 | 100% | 100% | 2 | 320
4 | Software Engineer (Backend) : Spring Boot | 4 | 1 | 50% | 62.5% | 1.125 | 180
5 | Sr. Software Engineer (Front-End) - React JS | 5 | 1 | 62.5% | 100% | 1.625 | 260
6 | Sr. Software Engineer (Front-End) - React JS | 4 | 1 |  | 100% | 1 | 160
7 | Sr. SQA | 5 | 1 | 50% | 100% | 1.5 | 240
8 | Sr. DevOps Eng. | 5 | 1 | 25% | 25% | 0.5 | 80
|  |  |  | 4.125 | 5.125 | 9.25 | 1480
[6 empty] | Avg | 160 | 1440 | Discount | 0%
[6 empty] | Discount | 0
[6 empty] | Total after Discount | 1480
[6 empty] | Avg | 160
RAP (Wordpress)
# | Resource | Rank | Unit price/hour in Euro | M1 | Total Efforts (mm & Cost) | Total cost in Euro
1 | Project Manager | 6 | 1 | 50% | 0.5 | 80
2 | Lead Software Engineer: Wordpress | 5 | 1 | 100% | 1 | 160
3 | Sr. SQA | 5 | 1 | 50% | 0.5 | 80
4 | Sr. DevOps Eng. | 5 | 1 | 25% | 0.25 | 40
|  |  |  | 2.25 | 2.25 | 360
[5 empty] | Avg | 160
[5 empty] | Discount | 0
[5 empty] | Total after Discount | 360
[5 empty] | Avg | 160

## Summary
Summary
# | Item information | UX/UI Design (man-day) | FE Development (man-day) | BE(API) Development (man-day) | QA (man-day) | Total (man-day) | Total (man-month) | Total with Extra (man-month) | Total Price (In Euro)
1 | #REF! | 2 | 4.5 | 6 | 2.5 | 15 | 0.75 | 0.89516
2 | Authentication, User & Role Management | 2.75 | 6 | 6 | 3.6056 | 18.3556 | 0.91778 | 1.0954
3 | Company & Multi-Tenancy Management | 2 | 4 | 6.25 | 2.9944 | 15.2444 | 0.76222 | 0.90975
4 | Learning Path / Course and Objective Management | 5.5 | 12.5 | 14.75 | 8.0056 | 40.7556 | 2.0378 | 2.4322
5 | Learning Path View & Update Progress | 1.25 | 4 | 4.75 | 2.4444 | 12.4444 | 0.62222 | 0.74265
6 | Team Leader Portal | 2.25 | 4.25 | 5.25 | 2.8722 | 14.6222 | 0.73111 | 0.87262
7 | Learner Portal | 1 | 2.5 | 3.25 | 1.65 | 8.4 | 0.42 | 0.50129
8 | Practical Trainer Portal | 0.75 | 2.25 | 3.25 | 1.5278 | 7.7778 | 0.38889 | 0.46416
9 | Dashboard & Email Notifications | 1.25 | 4 | 4 | 2.2611 | 11.5111 | 0.57556 | 0.68695
10 | Reporting & Analytics | 1.25 | 3.5 | 4 | 2.1389 | 10.8889 | 0.54444 | 0.64982
Total(man-day) |  | 20 | 47.5 | 57.5 | 30 | 155
Total(man-month) |  | 1 | 2.375 | 2.875 | 1.5 | 7.75 | 7.75 | 9.25
11 | Documentation (High level architecture, API Specification, Deploy documment) |  |  |  |  | 10 | 0.5
12 | Cloud |  |  |  |  | 10 | 0.5
13 | UAT | [5 empty] | 0
14 | Project Management |  |  |  |  | 10 | 0.5
| Grand Total(man-day) | 20 | 47.5 | 57.5 | 30 | 185
| Grand Total(man-month) | 1 | 2.375 | 2.875 | 1.5 | 9.25 | 9.25
|  |  | 2.625 | 3.125
# | Milestone | Effort (man-month) | Cost
1 | Project Initialization, Planning, Req. Understanding, Multi-language Suport & Architecture Design Authentication, User & Role Management Company & Multi-Tenancy Management Learning Path / Course and Objective Management (60%) | 4.3596 | 697.5415
2 | Learning Path / Course and Objective Management (40%) Learning Path View & Update Progress Team Leader Portal Learner Portal Practical Trainer Portal Dashboard & Email Notifications Reporting & Analytics | 4.8904 | 782.4585
Total |  | 9.25 | 1480

## Estimation_Custom
# | Module | Feature | Description | UI/UX (days) | Frontend (days) | Backend (days) | SQA (days) | Total (days)
1 | Project Initialization, Planning, Req. Understanding, Multi-language & Architecture Design |  |  | 2 | 4.5 | 6 | 2.5 | 15
|  | Project Setup & Environment Configuration | - Initialize project repository with version control (Git), branch strategy, and code review workflow. - Setup development, staging, and production environments. - Implement coding standards. - Setup project management tools and documentation repository. |  | 1 | 1 |  | 2
|  | Requirements Analysis | Requirements Analysis |  | 1.5 | 1.5 | 1.5 | 4.5
|  | Database Architecture & Schema Design | Design comprehensive database schema including all entities, relationships, and constraints. Create ER diagrams and data dictionary. Define indexing strategy, partitioning plan, and archival strategy. Design audit trail structure and temporal data management. |  |  | 1.5 |  | 1.5
|  | UI/UX Design initialization | Create UI/UX layout, intial preapartation | 1.5 |  |  |  | 1.5
|  | Multi-language support (English & Dutch) | - Internationalization (i18n) Architecture Design - UI Text Extraction - Language Resource Management - Language Selection Mechanism - Backend Localization - Content Localization | 0.5 | 2 | 2 | 1 | 5.5
2 | Authentication, User & Role Management |  |  | 2.75 | 6 | 6 | 3.6056 | 18.3556
|  | User Login/Logout | Secure authentication with session management | 0.5 | 0.75 | 0.75 | 0.48889 | 2.4889
|  | User Registration | Admin-controlled user registration with role assignment: User will receive an email for registration confirmation by setting new password | 0.5 | 1 | 1 | 0.61111 | 3.1111
|  | Forgot password | 1. Request forgot password: Send email to user 2. Reset password by using a link from email 3. Set new password | 0.25 | 0.75 | 0.75 | 0.42778 | 2.1778
|  | User Profile Management | View/edit user profile including password change | 0.25 | 0.75 | 0.75 | 0.42778 | 2.1778
|  | User Management | Complete user lifecycle management 1. New user with setting role - Sending email to complete the registration 2. Edit user - without password 3. Delete user 4. Password reset - Sending email to reset the user password 5. Searching user 6. Listing users with pagination and column sorting (parameterized listing page) | 0.5 | 1 | 1 | 0.61111 | 3.1111
|  | Feature Permissions Management | Feature wise permissions Features - Dashboard, User, Customer etc Permissions - View, Add, Edit, Delete, Download, Override etc. 1. Feture add with permissions 2. Edit 3. Delete 4. Listing with pagination and column sorting 5. Searching features | 0.25 | 0.5 | 0.5 | 0.30556 | 1.5556
|  | Role Management | Role definition and management module with granular permission assignment. Implements role hierarchy. 1. New Role 2. Edit 3. Delete 4. Listing with pagination and column sorting 5. Searching features | 0.25 | 0.75 | 0.75 | 0.42778 | 2.1778
|  | Access Control & Permissions | Fine-grained access control matrix mapping roles to features, data access levels, and approval authorities. Implements resource-level permissions, data segregation, and dynamic access evaluation. 1. Setting features into role | 0.25 | 0.5 | 0.5 | 0.30556 | 1.5556
3 | Company & Multi-Tenancy Management |  |  | 2 | 4 | 6.25 | 2.9944 | 15.2444
|  | Company Creation/Registration | Add multiple companies to the system - Create/Registration company - Deactive Companies | 0.75 | 1.5 | 1.75 | 0.97778 | 4.9778
|  | Company List & Search | - List of Companies - Search & Filter | 0.5 | 1 | 1 | 0.61111 | 3.1111
|  | Company Details View | Company Details View | 0.25 | 0.5 | 0.5 | 0.30556 | 1.5556
|  | Company Update | - Update logo - UPdate company details | 0.25 | 0.75 | 1 | 0.48889 | 2.4889
|  | Company-specific User Management | Invite users to specific companies and User Management | 0.25 | 0.25 | 0.5 | 0.24444 | 1.2444
|  | Data Isolation | Ensure company data separation |  |  | 1.5 | 0.36667 | 1.8667
4 | Learning Path / Course and Objective Management |  |  | 5.5 | 12.5 | 14.75 | 8.0056 | 40.7556
|  | Learning Path/Course Management | - Learning Path/Course Creation: Create new learning paths with job titles (e.g., "Measurement Watch 21/22") - Learning Path/Course Editor/Update - Learning Path/Course Details - Learning Path/Course List & Search | 1.5 | 4 | 4 | 2.3222 | 11.8222
|  | Category Management | Create/manage categories for objectives (CRUD) - List, Create, Details, Update & Delete | 0.5 | 1 | 1 | 0.61111 | 3.1111
|  | Learning Objective Management | Category wise Learning Objective (CRUD) - List, Create, Details, Update & Delete Learning Objective Creation Create objectives with title, description. KNOWLEDGE RESOURCES: video resource links, Rich text content management, link images, link documents (PDF, DOC, etc.), Link to external e-learning courses, Add learning activities to objectives, | 1 | 1.5 | 2 | 1.1 | 5.6
|  | Sub-learning Objectives Management | Hierarchical sub-objectives structure (CRUD) - based on learning objective | 0.5 | 1.5 | 2 | 0.97778 | 4.9778
|  | Standarded Managment | Standarded Managment - List, Create, Details, Update & Delete | 0.5 | 1.5 | 2 | 0.97778 | 4.9778
|  | Phase CRUD management | Central phase management for all courses and all sub learnings (Master data) Phase 1: Explaining Phase 2: Understanding (First) Phase 3: Demonstrating Phase 4: Doing Together Phase 5: Understanding (Second) Phase 6: Doing Independently | 0.75 | 1.5 | 2 | 1.0389 | 5.2889
|  | Comprehension Questions & Answers Management | Add comprehension questions & Answers to objectives (Text Base) | 0.75 | 1.5 | 1.75 | 0.97778 | 4.9778
5 | Learning Path View & Update Progress | Learner, Team lead (only view) and Trainer can update the progress |  | 1.25 | 4 | 4.75 | 2.4444 | 12.4444
|  | Course list for learner or progress view | Course list for learner or progress view | 0.25 | 0.5 | 0.75 | 0.36667 | 1.8667
|  | Course detail view | 1. Category wise learning objective view including percentage of learner | 0.5 | 1 | 1 | 0.61111 | 3.1111
|  |  | 2. Learning objective details view 2.1. Explanation 2.2. knowledge source 2.3. Phase wise sub learning list (with checkmark option) 2.4. Activities 2.5. Comprehension questions card view 2.6 Sub learning goal and Its Standards | 0.5 | 1.5 | 1.5 | 0.85556 | 4.3556
|  | Progress update/save of course detail | Trainer can check mark of phases of sub-learning. |  | 1 | 1.5 | 0.61111 | 3.1111
6 | Team Leader Portal |  |  | 2.25 | 4.25 | 5.25 | 2.8722 | 14.6222
|  | Course list for learner or progress view | Course list for learner or progress view | 0.5 | 1 | 1.5 | 0.73333 | 3.7333
|  | Course/Learning Path assignment | Assign course/Learning Path to learners | 0.25 | 0.5 | 0.5 | 0.30556 | 1.5556
|  | Trainer Assignment | Assign practical trainers to learners in Learning Path view detials | 0.25 | 0.5 | 0.5 | 0.30556 | 1.5556
|  | Trainer Invitation | Email invitation for trainers | 0.25 | 0.25 | 0.25 | 0.18333 | 0.93333
|  | Training Programs Overview & Progress Monitoring | Complete view of ongoing programs 1. List of course with total number of learner and overall progress 2. List of learner progress of the course) | 1 | 2 | 2.5 | 1.3444 | 6.8444
7 | Learner Portal |  |  | 1 | 2.5 | 3.25 | 1.65 | 8.4
|  | Course list for learner or progress view | Course list for learner or progress view | 0.25 | 0.5 | 0.75 | 0.36667 | 1.8667
|  | Course detail view | 1. Category wise learning objective view including percentage of learner | 0.125 | 0.25 | 0.25 | 0.15278 | 0.77778
|  |  | Start learning objective | 0.125 | 0.5 | 0.5 | 0.275 | 1.4
|  |  | 2. Learning objective details view 2.1. Explanation 2.2. knowledge source 2.3. Phase wise sub learning list 2.4. Activities 2.5. Comprehension questions card view, see actual answer 2.6 Sub learning goal and Its Standards | 0.25 | 0.75 | 1 | 0.48889 | 2.4889
|  |  | Submit comprehension question answer(text based, can also see the correct answer) | 0.25 | 0.5 | 0.75 | 0.36667 | 1.8667
8 | Practical Trainer Portal |  |  | 0.75 | 2.25 | 3.25 | 1.5278 | 7.7778
|  | Course list for learner or progress view | Course list for learner or progress view | 0.125 | 0.5 | 0.75 | 0.33611 | 1.7111
|  | Course detail view | 1. Category wise learning objective view including percentage of learner | 0.125 | 0.25 | 0.25 | 0.15278 | 0.77778
|  |  | 2. Learning objective details view 2.1. Explanation 2.2. knowledge source 2.3. Phase wise sub learning list (with checkmark option) 2.4. Activities 2.5. Comprehension questions card view 2.6 Sub learning goal and Its Standards | 0.125 | 0.5 | 0.75 | 0.33611 | 1.7111
|  | Start Course and Learn Objective | Start Course and Learn Objective | 0.125 | 0.5 | 0.75 | 0.33611 | 1.7111
|  | Phase update/save of course detail | Trainer can check mark of phases of sub-learning. | 0.25 | 0.5 | 0.75 | 0.36667 | 1.8667
9 | Dashboard & Email Notifications |  |  | 1.25 | 4 | 4 | 2.2611 | 11.5111
|  | Email Notifications | System-generated email notifications |  | 1 |  | 0.24444 | 1.2444
|  | Progress Alerts | Email Alerts for course completion to learner, team leaders | 0.25 | 1 | 1.5 | 0.67222 | 3.4222
|  | Admin Dashboard | 1. Number of course 2. Number of team lead 3. NUmber of learner/employee 4. Number of trainer NO Graph Considered. | 1 | 2 | 2.5 | 1.3444 | 6.8444
|  |  | No dashboard considered for super admin, leaner, leader, trainer. After login super admin will go to the company management page directly. After login of learner/leader/trainer will go Learning path view screen |  |  |  | 0 | 0
10 | Reporting & Analytics |  |  | 1.25 | 3.5 | 4 | 2.1389 | 10.8889
|  | Training Progress Reports [Candidate]- 2 Reports | Detailed progress reports [Progress reports of all candidates assigned ] REPORT 1: Specific LEARNING PATH PROGRESS REPORT Report Name: Specific_Learning_Path_Progress_Report Description: Progress of all candidates within a specific learning path REPORT 2: ALL LEARNING PATH PROGRESS REPORT Report Name: All Course Overview Reports Description: Progress of all candidates for all learning path | 1 | 2.5 | 3 | 1.5889 | 8.0889
|  | Export Functionality | Export reports to PDF/Excel | 0.25 | 1 | 1 | 0.55 | 2.8
|  |  | Total(man-day) | 20 | 47.5 | 57.5 | 30 | 155 | SQA Factor | 0.24444 | 0.24444
|  |  | Total(man-month) | 1 | 2.375 | 2.875 | 1.5 | 7.75

## Wordpress_Estimation
Workstream | Activities | Effort_Man_Days
Architecture & planning | Sizing, topology, security baseline, implementation plan | 1.5
Server preparation | Hardening, users/SSH keys, firewall, fail2ban, patching | 1.5
Web stack setup | Nginx/Apache, PHP-FPM, MariaDB/MySQL, TLS/SSL, domain & vhost | 1.5
WordPress setup | Installation, DB config, SMTP, permalinks, base plugins | 1.5
Masteriyo license purchase & activation | Purchase support, install, activate, verify license | 1.5
LMS baseline configuration | Course, lesson, quiz, enrollment, email templates, payment baseline | 2.5
Caching & performance tuning | FastCGI/page cache policy, Redis object cache, OPcache tuning | 2.5
Scalability readiness (100 users) | DB tuning, PHP workers, cron tuning, light load verification | 2.5
Backup | Scheduled backups, retention | 1
Security hardening | WP hardening, security headers, login protections, plugin audit | 2
UAT + go-live + handover | Functional validation, fixes, documentation, KT session | 2
TOTAL | Implementation effort total | 20